### Critical Path Analysis — Smart Hospital Project

### Critical Path Chain

| Order | Activity | Name | Finish Date |
| --- | --- | --- | --- |
| 1 | A1000 | Develop schedule baseline | 08-Jan-25 |
| 2 | A1080 | Conceptual design | 06-Feb-25 |
| 3 | A1090 | Schematic design | 14-Mar-25 |
| 4 | A1100 | Detailed design | 25-Apr-25 |
| 5 | A1160 | Submit building permit application | 09-May-25 |
| 6 | A1170 | Building permit approval (wait) | 24-Jun-25 |
| 7 | A1190 | Site clearing & grading | 16-Jul-25 |
| 8 | A1200 | Foundation excavation | 30-Jul-25 |
| 9 | A1210 | Foundation concrete pour | 20-Aug-25 |
| 10 | A1260 | Superstructure – Inpatient floors | 17-Nov-25 |
| 11 | A1270 | Building envelope – facade | 31-Dec-25 |
| 12 | A1300 | Electrical installation | 09-Mar-26 |
| 13 | A1360 | Network & cybersecurity infrastructure | 13-Apr-26 |
| 14 | A1330 | IoT patient monitoring installation | 26-May-26 |
| 15 | A1350 | EMR system integration | 23-Jul-26 |
| 16 | A1410 | Smart-systems testing & validation | 13-Aug-26 |
| 17 | A1440 | Staff training | 11-Sep-26 |
| 18 | A1450 | Facility handover & closeout | 25-Sep-26 |

Total project duration: 435 working days (Jan 2, 2025 to Sep 25, 2026 — roughly 21 calendar months)

### Three key insights you should be able to explain in an interview

#### 1. The critical path runs through regulatory approval, not specialized design

Interestingly, Structural Design (A1110) with 85 days of float and MEP Design (A1120) with 175 days of float are both not on the critical path — meaning those two design teams have plenty of schedule cushion. But the architectural sequence (Conceptual → Schematic → Detailed) → building permit submission → permit approval (a 30-day wait) sits directly on the critical path. This means bureaucracy and permit-waiting time, not engineering design work, is the project's real bottleneck.

#### 2. Almost the first six months have zero physical site work

Actual site work (Site Clearing) doesn't start until June 25, 2025 — meaning nearly the first half-year is consumed entirely by design and permitting. This is exactly where a professional PM would apply Fast Tracking: for example, instead of waiting for Detailed Design to fully complete, the building permit application could be submitted based on Schematic Design (which finishes earlier), while Detailed Design continues in parallel. This could shave months off total project duration — a classic interview question: "How would you compress this schedule?"

#### 3. The Smart-Systems chain is a hidden bottleneck

Even though IoT, BMS, and EMR look like small individual work packages (30–40 days each), because of their chained dependencies (Network → IoT → EMR → Testing), this segment stays on the critical path from March 10, 2026 to August 13, 2026 — meaning roughly the last five months of the project are driven by the smart-systems integration, not physical construction.