# MediCore Smart General Hospital

## Project Management Practice Exercise — Progress Summary

This document summarizes the project management exercise developed for internship preparation: mastering MS Project / Primavera P6 workflows through the full lifecycle of a fictional smart-hospital construction project, from Business Case through Cost Baseline.

# 1. Project Overview (from Project Charter)

- Project: Construction of a 200-bed, ~500,000 sq ft smart general hospital

- Sponsor: MediCore Health Group Board

- Approved capital budget (Order-of-Magnitude, Charter): $300,000,000 USD (-25%/+75%)

- Schedule constraint per Charter: substantial completion within 42 months of Notice to Proceed

- Business Case selection: NPV analysis favored the smart-technology investment option over incremental renovation

# 2. Organizational Breakdown Structure (OBS)

Top node: Enterprise, with eight functional managers directly beneath it (no separate Project Manager node exists in the OBS as built):

- Design Manager — Lead Architect, Structural Engineer, MEP Engineer, Medical Planning Specialist

- Construction Manager — Site Superintendent, Structural/MEP/Finishing Subcontractors, Site Safety Coordinator

- Smart-Systems / IT Integration Manager — EMR Integration Lead, IoT/BMS Lead, Network & Cybersecurity Specialist

- Procurement Manager — Buyer, Contract Administrator, Vendor/Supplier Coordinator

- QA/QC Manager — Quality Inspectors, Materials Testing Lab Officer

- HSE Manager — Safety Officers, Environmental Compliance Officer

- Commissioning & Accreditation Manager — Commissioning Engineer, Regulatory/Accreditation Liaison

- Financial Controller — Cost Controller, Accounts Payable Officer

# 3. Work Breakdown Structure (WBS) — Responsible Manager Mapping

| WBS | Name | Responsible Manager |
| --- | --- | --- |
| HCB | Hospital construction building | Enterprise |
| HCB.1 | Project Management | Enterprise |
| HCB.2 | Design | Design Manager |
| HCB.3 | Permits & Regulatory Approval | Commissioning & Accreditation Manager |
| HCB.4 | Site Preparation & Civil Works | Construction Manager |
| HCB.5 | Structural Construction | Construction Manager |
| HCB.6 | MEP Installation | Construction Manager |
| HCB.7 | Smart-Systems Integration | Smart-Systems / IT Integration Manager |
| HCB.8 | Interior Finishing & Medical Fit-out | Construction Manager (mixed) |
| HCB.9 | Commissioning & Testing | Commissioning & Accreditation Manager (mixed) |
| HCB.10 | Accreditation & Handover | Commissioning & Accreditation Manager (mixed) |

# 4. Schedule Summary

43 execution activities (A1000–A1450) were defined, sequenced with FS/SS/FF relationships, and scheduled against a US 5-day calendar with federal holiday exceptions (2025–2026). After resolving open-end activities and redundant logic, the schedule was calculated (F9).

- Project start: January 2, 2025

- Project finish: September 25, 2026

- Total duration: 435 working days (~21 calendar months)

## Critical Path

| Activity ID | Activity Name | Finish Date |
| --- | --- | --- |
| A1000 | Develop schedule baseline | 08-Jan-25 |
| A1080 | Conceptual design | 06-Feb-25 |
| A1090 | Schematic design | 14-Mar-25 |
| A1100 | Detailed design | 25-Apr-25 |
| A1160 | Submit building permit application | 09-May-25 |
| A1170 | Building permit approval (wait) | 24-Jun-25 |
| A1190 | Site clearing & grading | 16-Jul-25 |
| A1200 | Foundation excavation | 30-Jul-25 |
| A1210 | Foundation concrete pour | 20-Aug-25 |
| A1260 | Superstructure – Inpatient floors | 17-Nov-25 |
| A1270 | Building envelope – facade | 31-Dec-25 |
| A1300 | Electrical installation | 09-Mar-26 |
| A1360 | Network & cybersecurity infrastructure | 13-Apr-26 |
| A1330 | IoT patient monitoring installation | 26-May-26 |
| A1350 | EMR system integration | 23-Jul-26 |
| A1410 | Smart-systems testing & validation | 13-Aug-26 |
| A1440 | Staff training | 11-Sep-26 |
| A1450 | Facility handover & closeout | 25-Sep-26 |

Key insight: the critical path runs primarily through design → permitting → foundation → the longest structural wing → electrical → the smart-systems integration chain — not through the specialty design disciplines (Structural Design and MEP Design both carry large float).

# 5. Resource & Cost Summary

Resources were defined in three categories — Labor and Nonlabor (rate per day) and Material (Lump Sum, Price/Unit) — and assigned to activities. Material costs required fractional Budgeted Units (share of 1.0) rather than day-based units.

| WBS Branch | Budgeted Total Cost |
| --- | --- |
| Project Management | $1,597,500 |
| Design | $457,500 |
| Permits & Regulatory Approval | $85,500 |
| Site Preparation & Civil Works | $6,251,500 |
| Structural Construction | $91,301,000 |
| MEP Installation | $61,046,000 |
| Smart-Systems Integration | $23,125,000 |
| Interior Finishing & Medical Fit-out | $39,188,000 |
| Commissioning & Testing | $147,000 |
| Accreditation & Handover | $60,000 |
| TOTAL | $223,259,000 |

# 6. Open Item — Cost Baseline vs. Charter Budget

The bottom-up estimate ($223.3M) is meaningfully below the Charter's Order-of-Magnitude authorization ($300M), landing near the low end of the Charter's stated -25%/+75% accuracy range. Rather than artificially forcing the numbers to $300M with a fabricated contingency line, this gap has been intentionally left open as a governance decision point to be resolved at the next stage (Sponsor review: re-baseline down, or formally allocate the ~$77M difference as Management Reserve outside the Cost Baseline).

# 7. Next Steps

- Resolve the Cost Baseline vs. Charter Budget variance (Sponsor decision point)

- Build the time-phased S-Curve (Planned Value distribution)

- Develop the Risk Register in detail and link risks to WBS packages

- Prepare a mock EVM tracking exercise (PV/EV/AC, CPI/SPI) once a baseline is set